## Sheet1
Task name | Estimated time (h) | Time spent | Responsable | Details | Cost (€) | State
Poc 1 | NaN | 15h | Ambroise | First version of the POC done a few weeks ago | 450 | Done
Generate a YAML file from node.js and create a function to do it dynamically | 3 | 3 | Ambroise | The function will take two parameters: data: JS object that contains the data to write in the YAML file path: The path where to write the file. | 90 | Done
Analyse all the different scenarios which would impact the generated Ansible Cli command (extra-vars) | 1.5 |  | Ambroise | Depending on the module, (hsrp, ospf, svi) we will have to generate some extra-vars in the cli command. All the possibilities are unclear at the moment and it is needed to clarify what must be done depending on the different scenarios. | 45 | Not started
Generate and call from node an Ansible command based on user inputs | 2 |  | Ambroise |  | 60 | Not started
Discussions and meetings (emails, skypes) | 6 | 2h for the moment |  | Time spent during oral meetings, discussion, emails and so on. | 180
Use Restify node client to receive POST requests and generate YAML file vlan id, vlan name) | 3 | 1.5 | Ambroise |  | 90 | Done
Test: Generate a YAML file | 1 | 1.5 | Ambroise |  | 30 | Done
Test: Use Restify node client | 1 | 1 | Ambroise |  | 30 | Done
Test: Generate the Ansible command | 1 |  | Ambroise |  | 30 | Not started
0
0
0
0
0
0
0
0
0
0
Total: (Includes +3% for Paypal) | 18.5 |  |  |  | 1035.15
Payments: (€)
194.5